## Sheet1
Task Name | Description | Deadline | Status
Infrastructure Setup | Provision cloud resources, networking, load balancers, DNS | 2026-04-05
Security Configuration | Configure TLS, encryption at rest, IAM roles, secrets management | 2026-04-08
Authentication & Authorization | Implement JWT/OAuth, RBAC, service accounts | 2026-04-10
CI/CD Pipeline Setup | Set up automated deployments, staging/prod environments, rollback strategy | 2026-04-12
Testing Phase | Unit, integration, security, and performance testing | 2026-04-18
Data Migration | Migrate and validate data, perform backups | 2026-04-20
Monitoring & Logging Setup | Configure logging, monitoring tools, and alerts | 2026-04-22
Internal Validation (Staging) | Deploy to staging, internal testing, bug fixes | 2026-04-24
Beta Release | Release to beta users, monitor feedback and performance | 2026-04-27
Production Launch | Go live, switch DNS, enable full access | 2026-04-30
Post-Launch Support | Monitor system, fix bugs, optimize performance | 2026-04-30